## Trigger Event Management
Construction Procurement - Trigger Event Management - Step by Step Guide Contact: Heidi Duckworth Category Specialist WoG Construction Procurement Accreditation & Assurance Programs Heidi.Duckworth@finance.nsw.gov.au
Requirement | # | Step | Reference | Deliverable / Action | Documents / Templates / Formats / Links | Process | Interested Parties & End Recipient
Trigger Event Management | 1 | Identify | 5.3.1 | Identify the type of trigger event. | Refer to 5.3.1 in Accreditation Program Requirements for Construction Procurement |  | Accredited agency
| 2 | Determine | 5.3.2 | Agency determines scope and severity of trigger event. Agency may engage independent advisor to assist with determination. |  |  | Accredited agency | he agency must determine the scope and severity of the trigger event. If appropriate, the agency may engage an independent advisor to help make this determination.
| 3 | Complete | 5.3.2 | Complete the Trigger Event Management Plan to identify remedial actions to address the trigger event. | Refer Trigger Event Management Plan template on BUY.NSW |  | Accredited agency | The agency must complete the trigger event management plan XLSX, 66.59 KB document in the toolkit to identify remedial actions to address the trigger event.
| 4 | Approve | 5.3.2 | Submit Trigger Event Management Plan to Agency Head(s) for internal approval. |  |  | Accredited agency & Agency Head(s) | The agency head(s) must approve the plan.
| 5 | Endorse | 5.3.2 | Provide a high level overview of trigger event and the approved Trigger Event Management Plan to the Risk and Compliance Subcommitee for endorsement. If required, the RCS may send the Trigger Event Management Plan to the NSW Procurement Board for review.(NSWPB) | Refer Trigger Event Management Plan template on BUY.NSW |  | Category Specialist and Risk and Compliance Subcommitee | The agency must submit the plan to the Risk and Compliance Subcommitee (RCS) for review as soon as reasonably possible. Once the RCS reviews and endorses the plan, the agency can begin to implement the plan. If necessary, RCS may escalate the plan to the NSW Procurement Board for review. Depending on the nature of the trigger event and the agency’s plan, the board may decide to conduct a targeted review or withdraw the agency’s accreditation.