## Sheet1
Construction Procurement - Assurance Process - Step by Step Guide Contact: Heidi Duckworth Category Specialist WoG Construction Procurement Accreditation & Assurance Programs Heidi.Duckworth@pwa.nsw.gov.au
Requirement | # | Step | Reference | Deliverable / Action | Documents / Templates / Formats / Links | Process | Interested Parties & End Recipient
Assurance Process | 1 | Justify | 3.1 | Unaccredited agency must develop a Business Case to justify the procurement. | Refer to Government Business Case Guidelines on BUY.NSW | Refer to NSW Treasury’s NSW Government Business Case Guidelines for information on developing a business case | Unaccredited agency
| 2 | Plan | 3.2 | Unaccredited agency must draft a Construction Procurement Plan. This plan is specific to the procurement activities at the project level. | Refer to the Construction Procurement Plan Guidelines on BUY.NSW | Refer to the Construction Procurement Plan Guidelines for further information about developing a construction procurement plan. | Unaccredited agency
| 3 | Assess | 3.3 | Unaccredited agency must assess the level of risk associated with the construction project. The Project Risk Profile Tool must be used. | Refer Project Risk Profile Tool on BUY.NSW |  | Unaccredited agency
| 4 | Engage | 4 | Unaccredited agency must engage an accredited agency to provide assurance for the construction project. |  |  | Accredited agency & unaccredited agency
| 5 | Establish Responsibilities | 5 | Accredited and unaccredited agencies have a number of responsibilities in relation to compliance with legislation, policies, procedures and risk management when entering into assurance. |  |  | Accredited agency & unaccredited agency
| 6 | Review | 5.1 | The accredited agency who has been engaged to provide the assurance must review the Business Case, Project Risk Profile Tool and Construction Procurement Plan. |  |  | Accredited agency
| 7 | Decision | 5.2 | After the accredited agency reviews the Business Case, Project Risk Profile Tool and Construction Procurement Plan, the accredited agency will decide if they will provide assurance and what type of assurance is appropriate for the project. |  |  | Accredited agency
| 8 | Formalise | 5.3 | The accredited agency who has been engaged to provide the assurance must complete a formal assurance letter and send it to the unaccredited agency. | Refer Construction Assurance Letter template on BUY.NSW |  | Accredited agency & unaccredited agency
| 9 | Source & Manage | 6.1 | Unaccredited agency is now able to conduct the "source" and "manage" phases of the construction procurement. |  |  | Unaccredited agency
| 10 | Complete & Report | 6.2 | Unaccredited agency must complete Project Completion Summary Report at end of construction project. | Refer Project Completion Summary Report on BUY.NSW | Submit the Project Completion Summary Report to Category Specialist | PWA & NSWPB