## Introduction
Project Risk Profile Tool
Assurance Process for Construction Procurement
This document forms part of the Assurance Process for Construction Procurement.
Before completing this document, please read the Assurance Process for Construction Procurement.
Overview
Before seeking assurance from an accredited agency to undertake construction procurement activities valued over $1.3 million, an unaccredited agency must complete a risk assessment of the procurement using this Project Risk Profile Tool. The unaccredited agency will send this Tool to the accredited agency providing assurance. The accredited agency will then validate the unaccredited agency's self-assessment of the overall risk score of the procurement.
Using this document
Contact information about both the unaccredited agency and the accredited agency providing assurance should be entered into Tab 1 (Contact information). The unaccredited agency enters information about the priority and risk levels of the project in Tab 2 (Data Entry). Tab 3 (Appendix A) provides important information about the four criteria against which the risk of the project is assessed. Tab 4 (Appendix B) suggests appropriate forms of assurance based on the overall weighted risk score and risk range of the procurement activity.

## 1. Contact information
1. Contact Information
Name of unaccredited agency | Insert name of unaccredited agency
Name of unaccredited agency representative | Insert name of agency representative
Unaccredited agency representative email address | Insert email address of agency representative
Unaccredited agency representative contact number | Insert contact number of agency representative
Name of accredited agency providing assurance | Insert name of accredited agency
Accredited agency representative name | Insert name of agency representative
Accredited agency representative email address | Insert email address of agency representative
Accredited agency representative contact number | Insert contact number of agency representative

## 2. Data entry
2. Data Entry
Key
Unshaded |  | Do not enter data.
Enter free-form text. Adjust row height to make all text visible.
Select from drop-down list.
Do not enter data. This field will automatically populate.
Tips
Where you are required to enter free-form text: - Adjust row height to make all text visible. - Alt + Enter creates a new paragraph in a cell. - Alt + 7 (using the numeric pad), followed by a space, creates a bullet point in a cell.
Step 1: Assessing the priority and preliminary risk potential
Q1.1 | Level of government priority |  | - | Insert comments to support/clarify assessment. Include responses to the example questions to be considered when addressing the criteria, as set out in Appendix A.
Please see definition in Appendix A.
Q1.2 | Interface complexity risk |  | - | Insert comments to support/clarify assessment. Include responses to the example questions to be considered when addressing the criteria, as set out in Appendix A.
Please see definition in Appendix A.
Q1.3 | Procurement complexity risk |  | - | Insert comments to support/clarify assessment. Include responses to the example questions to be considered when addressing the criteria, as set out in Appendix A.
Please see definition in Appendix A.
Q1.4 | Agency capability risk |  | - | Insert comments to support/clarify assessment. Include responses to the example questions to be considered when addressing the criteria, as set out in Appendix A.
Please see definition in Appendix A.
NOTE: The lower the agency capability, the higher the risk.
Step 2: Calculating the preliminary project risk
Q2.1 | Rating - Level of government priority |  | - Level of government priority |  | -
Q2.2 | Rating - Interface complexity |  | - Interface complexity risk |  | -
Q2.3 | Rating - Procurement complexity |  | - Procurement complexity risk |  | -
Q2.4 | Rating - Agency capability |  | - Agency capability risk |  | -
Q2.5 | Overall weighted risk score
Q2.6 | Overall risk range |  |  |  |  | Appendix B suggests appropriate forms of assurance based on the risk score and risk range of the project.
Step 3: Additional considerations and adjusting the risk range
Q3.1 | Are there any additional risk considerations that were not taken into account in Steps 1 and 2? Additional risk considerations could include risk of reputational damage, unknown project governance arrangements, lack of planning, lack of delivery skills, lack of resources, and critical start or completion date.
-
Q3.1a | If yes, please identify all additional risk considerations and the proposed strategies to mitigate these risks. Please attach any relevant documentation.
Q3.2 | In light of the answer to Q3.1, does the preliminary project risk range require adjustment?
-
Q3.2a | If yes, please select proposed adjusted risk range.
-

## 3. Appendix A
3. Appendix A: Description of risk criteria
| Criteria and weighting | Sub-Criteria | Risk score | Example questions to be considered
1 | Government priority Weighting in overall risk score: 25% The level and timing of project or program priority, where: • The level of priority for a project is specifically mandated (or where a ministerial authority has mandated that a project is a priority) in documents such as the NSW Budget, Premier’s Priorities, State Infrastructure Strategy, Election Commitment, or is a response to a legislative change. Alternatively, the project is an enabler of a mandated priority project. • The timing of the priority project can be either within or outside the Forward Estimates period and relates to planning/development commencement, construction commencement or construction completion. | Extremely Low Government priority Not a documented Government or agency priority | 0 | Government priority indicators • Has the project been specifically mandated in the NSW Budget? • Has the project been specifically mandated in the Premier's Priorities or equivalent? • Is the project linked to a project specifically mandated in any Government endorsed whole of Government plan, for example, the State Infrastructure Strategy? • Is the project an election commitment? • Is the project a response to a legislative change? • Is the project an enabler of a mandated priority project? • Has there been a Ministerial announcement regarding the project? • Has the project received significant regional or state-wide media coverage? • Is the project a strategic priority for Government? • Is the project a strategic priority for the agency or department? • Does accountability for the project reside with Cabinet, a Cabinet Committee or a Minister? Project timing indicators • Has planning or implementation of the project already commenced? • Will the project be fully operational within 12 months? • Will the project be fully operational within the forward estimates period?
|  | Very Low Government Priority Agency priority in Agency Strategic Plan over the next 10 years | 1
|  | Low Government priority Mandated priority project, and final business case and construction to commence outside forward estimates but within the next 3-6 years beyond forward estimates | 2
|  | Medium Government priority Mandated priority project, and final business case or construction to be completed outside forward estimates but within the next 1-2 years beyond forward estimates | 3
|  | High Government priority Mandated priority project, and final business case or construction to commence within forward estimates | 4
|  | Very High Government priority Mandated priority project, and final business case or construction to be completed within forward estimates | 5
2 | Interface complexity Weighting in overall risk score: 25% The extent to which the projector program’s success will depend on the management of complex dependencies with other: • Institutions - certain bodies are contributing to the funding of the project or will be given operational responsibility; and/or • Projects or services – there are fundamental interdependencies with other projects or services that will directly influence the scope and cost of the project. | Extremely low interface complexity risk No interface complexity | 0 | Interface Complexity indicators • Are other entities contributing to the funding of the project? • Will other entities be given full or partial operational responsibility for the project? • Are there other projects, program or services that will directly influence the scope and cost of the project? • Does the project involve multi-agency delivery? • Are the anticipated project benefits dependent on another project, program or service? • Does the project involve significant integration (IT or otherwise) with other projects, programs or services? • Will members of the public be directly impacted by this project? • Will the private sector be directly impacted by this project? • Will the public sector (outside of the delivery agency) be directly impacted by this project? • Will the project involve external delivery partners?
|  | Very low interface complexity risk • Very little or infrequent interface with entities; or • Very little interdependence on other projects or services | 1
|  | Low interface complexity risk • Institutional interface with 1 entity; or • Minor interdependence with other projects or services | 2
|  | Medium interface complexity risk • Institutional interface with 1 entity (Federal, local or private); or • Some interdependencies with other projects or services | 3
|  | High interface complexity risk • Institutional interface with 2 entities (Federal, local or private); or • Important interdependencies with other projects or services | 4
|  | Very high interface complexity risk • Institutional interface between Federal, local and private entities; or • Fully interdependent on other projects or services | 5
3 | Procurement complexity Weighting in overall risk score: 20% The extent to which a project or program requires, sophisticated, customised or complex procurement methods (non-traditional), thereby increasing the need for a careful assessment and management of risk. Procurement complexity may also be influenced by the extent of agency experience and capability. For example, some procurement methods (e.g. ECI) may be used more commonly by some agencies and represent a lower procurement risk. | Extremely low procurement complexity risk No procurement complexity, for example, routine procurement method for a routine infrastructure product | 0 | Procurement Complexity indicators • Will/could the project use a non-traditional (complex or customised) procurement method? • Does the agency have experience in the proposed procurement method? • Does the agency have a high level of capability in the proposed procurement method? • Is the service contract likely to be >10 years? • Is the project dependent on input from an immature/inexperienced market segment?
|  | Very low procurement complexity risk Business as usual procurement, for example, Design and Construct | 1
|  | Low procurement complexity Minor procurement complexity, for example, Directly Managed Contract | 2
|  | Medium procurement complexity risk Some procurement complexity, for example, Early Contractor Involvement | 3
|  | High procurement complexity risk Unconventional complex procurement, for example, an Alliance or hybrid Alliance | 4
|  | Very high procurement complexity risk Highly complex procurement, for example, Public Private Partnership (PPP), or a Hybrid that includes a PPP | 5
| Agency capability: 20% The extent to which the sponsor agency has demonstrated capability (skills and experience), or can access through recruitment or procurement the required capability in the development and/or delivery of the type of project or program proposed and/or its delivery strategy. | Very high agency capability risk
High agency capability risk
Medium agency capability risk
Low agency capability risk
Very low agency capability risk
Extremely low agency capability risk
4 | Agency capability Weighting in overall risk score: 30% The extent to which the sponsor agency has demonstrated capability (skills and experience), or can access through recruitment or procurement the required capability in the development and / or delivery of the type of project or program proposed and/or its delivery strategy. | Extremely low agency capability risk Very routine projects | 0 | Agency Capability indicators • Are the operations and outcomes of the project aligned to the agency's core business and strategic objectives? • Does the organisation have a successful track record of delivering initiatives of a similar scope and/or scale? • Has the organisation been established within the past 12 months? • Does the organisation have ongoing stable operations? • Does the organisation have an ongoing, stable source of funding? • Has the organisation been established for the purpose of delivering this project? • Has the organisation delivered a project that has been subject to a major recurrent Gateway review? • Will the agency be delivering this project in partnership with a more experienced delivery partner? • Does the agency have in-house capability to deliver the project or will the agency be contracting/recruiting • Does the agency have the capability to manage the ongoing activities of the project after the procurement stage?
|  | Very low agency capability risk Business-as-usual projects | 1
|  | Low agency capability risk Multiple recurring projects | 2
|  | Medium agency capability risk At least 5 projects of this type over the last 5 years. | 3
|  | High agency capability risk Few projects of this type previously delivered over the last 10 years | 4
|  | Very high agency capability risk No projects of this type previously delivered over the last 10 years | 5

## 4. Appendix B
4. Appendix B: Suggested forms of assurance
Various Considerations
The table below suggests appropriate forms of assurance based on the weighted risk score of the project. These suggestions are not binding. To ultimately decide which form of assurance is appropriate for the unaccredited agency's project, the accredited agency should also consider: • Whether the unaccredited agency’s procurement plan complies with the NSW Procurement Policy Framework and all other relevant legislation, policies and frameworks; • Whether the unaccredited agency has the capability and capacity to deliver the construction project in an efficient and effective manner, by sourcing the required construction services and effectively managing the project, in accordance with its procurement plan; and • Any other relevant considerations that are specific to the project.
Weighted Risk Score Ranges | Suggested Forms of Assurance
0.0 – 2.0 | Accredited agency provides formal assurance with minimal or no conditions.
2.1 – 2.5 | Accredited agency provides formal assurance with some general conditions.
2.6 – 4.0 | Accredited agency provides formal assurance with specific conditions.
4.1 – 5.0 | Accredited agency provides formal assurance on the condition that either: • The accredited agency will support the unaccredited agency to find an appropriate third party to procure and deliver the project on behalf of the unaccredited agency; or • The accredited agency procures and delivers the project on behalf of the unaccredited agency.

## Hidden Matrices (hidden)
APPENDIX B – Risk score matrix and risk profile criteria
| Criteria | Weighting | Criteria | Priority and Risk level | Score
| Government priority | 25% | Government priority | Very High Government priority | 5
| Interface complexity | 25% |  | High Government priority | 4
| Procurement complexity | 20% |  | Medium Government priority | 3
| Agency capability | 30% |  | Low Government priority | 2
|  |  |  | Very Low Government Priority | 1
|  |  |  | ExtremelyLow Government priority | 0
|  |  | Interface complexity | Very high interface complexity risk | 5
|  |  |  | High interface complexity risk | 4
|  |  |  | Medium interface complexity risk | 3
|  |  |  | Low interface complexity risk | 2
|  |  |  | Very low interface complexity risk | 1
|  |  |  | Extremely low interface complexity risk | 0
|  |  | Procurement complexity | Very high procurement complexity risk | 5
|  |  |  | High procurement complexity risk | 4
|  |  |  | Medium procurement complexity risk | 3
|  |  |  | Low procurement complexity risk | 2
|  |  |  | Very low procurement complexity risk | 1
|  |  |  | Extremely low sourcing complexity risk | 0
|  |  | Agency capability | Very high agency capability risk | 5
|  |  |  | High agency capability risk | 4
|  |  |  | Medium agency capability risk | 3
|  |  |  | Low agency capability risk | 2
|  |  |  | Very low agency capability risk | 1
|  |  |  | Extremely low agency capability risk | 0
Office Use only below this line
Rating Lookup Table
| 0 | 0.0 – 2.0
| 2.1 | 2.1 – 2.5
| 2.6 | 2.6 – 4.0
| 4.1 | 4.1 – 5.0
tbllevelratings
| Level | Rating
| Extremely low | 0
| Very low | 1
| Low | 2
| Medium | 3
| High | 4
| Very high | 5

## Hidden Drop down lists (hidden)
DROP DOWN LISTS
Responsible Minister | Department | Capital asset type | Project_program priority | ETC Band | Risk Potential | Yes/No | Yes/No | Yes/No/Maybe | Yes/No/Developed | Yes-in place/Being developed/No | Tier | Health Checks | Frequency | Check |  | Project phase | Funding approval
Attorney General | Education | 1. Infrastructure Project | State Budget Allocation | <$100 M | - | - | Yes | Yes | Yes | Yes-in place | Tier 1 | None | Monthly | P | Very high change complexity risk | Concept development | None approved
Minister for Aboriginal Affairs | Family and Community Services | 2. Property Development | Strategic Plan | $100M – $250M | Extremely low | Yes | No | No | No | Being developed | Tier 2 | 1 | Quarterly | O | High change complexity risk | Preliminary Business Case | Approved for development of Strategic Business Case
Minister for Aging | Finance, Services and Innovation | 3. Equipment | Election Commitment | $250M – $500M | Very low | No | N/A | Possibly | Being Developed | No | Tier 3 | 2 | None |  | Medium change complexity risk | Business Case | Approved for development of Final Business Case
Minister for Corrections | Health | 4. ICT Project | Ministerial Commitment | >$500M | Low |  |  | N/A | N/A |  | Tier 4 | 3 | Other |  | Lower change complexity risk | Pre-execution | Funding Approved
Minister for Counter Terrorism | Industry, Skills and Regional Development | 5. Other capital expenditure | Legislation |  | Medium | [6 empty] | Greater than 3 |  |  | Very low change complexity risk | Tender evaluation
Minister for Disability Services | Justice |  | Other |  | High | [6 empty] | Unknown |  |  | Extremely low change complexity risk | Pre-commissioning (build/test)
Minister for Early Childhood Education and Assistant Minister for Education | Planning and Environment |  |  |  | Very high | [10 empty] | Implementation
Minister for Education | Premier and Cabinet | [14 empty] | Closure
Minister for Emergency Services | Transport for NSW
Minister for Energy and Utilities | Treasury |  |  |  | -
Minister for Family and Community Services | Other |  |  |  | Extremely low
Minister for Finance, Services and Property |  |  |  |  | Very low
Minister for Health |  |  |  |  | Low | Funding Source |  |  |  | Example |  | Changetier | Yes | No
Minister for Heritage |  |  | Gate 0 - Project Justification |  | Medium | Budget funded-approved |  |  |  | selection 1 |  | Yes | -
Minister for Housing |  |  | Gate 1 - Strategic Assessment |  | High | Budget funded-to be approved |  |  |  | selection 2 |  | No | 0.0 - 2.0
Minister for Industrial Relations |  |  | Gate 2 - Business Case |  | Very high | Agency funded |  |  |  | selection 3 |  |  | 2.1 - 2.5
Minister for Innovation and Better Regulation |  |  | Gate 3 - Pre-Tender/Pre-execution |  |  | Partly Budget funded-approved | [6 empty] | 2.6 - 4
Minister for Lands and Forestry |  |  | Gate 4 - Tender Evaluation |  |  | Partly Budget funded-to be approved | [6 empty] | 4.1 - 5
Minister for Local Government |  |  | Gate 5 - Pre-Commissioning |  |  | Other
Minister for Medical Research |  |  | Gate 6 - Post-Implementation
Minister for Mental Health
Minister for Multiculturalism
Minister for Planning
Minister for Police
Minister for Primary Industries
Minister for Racing
Minister for Regional New South Wales
Minister for Regional Water
Minister for Resources
Minister for Roads, Maritime and Freight
Minister for Skills
Minister for Small Business
Minister for Social Housing
Minister for Sport
Minister for the Arts
Minister for the Environment
Minister for the Prevention of Domestic Violence and Sexual Assault
Minister for Tourism and Major Events and Assistant Minister for Skills
Minister for Trade and Industry
Minister for Transport and Infrastructure
Minister for Veterans Affairs
Minister for WestConnex
Minister for Western Sydney
Minister for Women
Premier
Treasurer
Other