## OBJECTIVE
Tool for Risk Identification in ICT/Digital Sourcing
Identification, assessment and treatment of risks are integral to the planning, sourcing and managing stages of the ICT procurement process. By identifying potential risks during the planning stage, decision-makers can formulate a plan to mitigate them. The effort expended in managing risks in a procurement process should be consistent with the estimated procurement cost and complexity, significance and nature of the process. It is the nature of risk and risk management that, sometimes, unexpected problems occur. When this happens it is important that the reasons and circumstances are identified and documented, and taken into account with future risk analyses including updating guidance documents accordingly. This tool is only a guidance to assist you in identifying risks when procuring an ICT/Digital solution. This tool is not intended to be exhaustive nor mandatory. Agencies are reminded to follow their internal risk managementpolicies, framework and processes. All risk management decisions including risk identification, assessment and management should be recorded. This provides an accountability trail.
Objective

## Software & Cloud
Category | Risk Type | Considerations
Software / Cloud | Service Level Arrangement | Is there an appropriate service level arrangement with the supplier to drive performance and system uptime? For example, if an agency wants to use a cloud service and it requires a certain level of performance - how can we ensure the supplier does the right thing and maintains the service level.
Software / Cloud | Data Sovereignty | Is the data subject to the laws of Australia? It is in the Agencies' best interest to ensure that the data that might be part of a project, is subject to the laws of Australia and not to another country. For example - backing up data in another country could lead to potential issues if there is a system failure.
Software / Cloud | Data Security | Where will the Agency's Data be stored ? List locations (countries and states) and describe data storage/processing systems What physical and technological security and breach of security response arrangements will be in place at the locations where the Agency’s Data will be stored ? Is the data encrypted when it is collected/created or stored ? How is this encryption performed (including cipher and key length) ? How are the encryption keys secured ? At what points is unencrypted Data stored before it is provided to the Department ? How is user authentication performed ? Can the Agency be provided with access to the policies and standards relating in the protection of the Agency's data, systems and the underlying infrastructure providing the services Which supplier personnel will have access to the Agency's Data ? Have these personnel cleared criminal history checks ? Has the supplier encountered breaches of security ? If so, how did they respond ? Can the Agency's personnel or contractor inspect, on reasonable notice, the premises where the Agency's Data will be stored to verify that the supplier is complying with its obligations ?
Software / Cloud | Cyber Security Plan | Do you have the appropriate cyber security plans in place for the protection of data? This means ensuring that suppliers have a cyber security plan in place and is used. This plan is something that should be continuously improved so that it protects the agency from hackers, data leaks, etc.
Software / Cloud | Legal | Have you reviewed the suppliers' terms adequately? If there is provision to include supplier terms and those terms refer to a particular hyperlink then the risk is that supplier terms may change over the course of the contract. For example, half way through a three year contract the supplier terms change in the hyperlink provided. In these situations agencies should print out exactly what the terms are and attach that to the contract and set this as a baseline.
Software / Cloud | Reporting | What type of reporting is required for your procurement? Ensure that we can obtain the type of reporting we need to either drive performance or calculate procurement benefits
Software / Cloud | Corruption/ Loss of Data | What physical and technological protections does the supplier have in place to minimise data corruption and loss of Data ? How does the supplier back up Data ? If so, what type of backups are used ? How frequent are the backups ? Will the supplier segregate the Agency’s Data from other customers’ Data ? If so, describe how. If not, describe controls which will prevent the unauthorised access or corruption of the Agency’s Data by the supplier's customers How does the supplier propose to recover Data, if Data is corrupted or lost?
Software / Cloud | Efficiency & Reliability of Services | What are the supplier’s technical offerings? How is the supplier’s infrastructure maintained ? What physical and technological protections does the supplier have in place to reduce the risk of service disruptions and downtime ? What mechanisms does the supplier have in place in relation to disaster recovery to ensure services are quickly restored if there are availability and reliability issues ? What type of business continuity arrangements does the supplier have to ensure services continue to operate ? What support services (e.g. helpdesk) does the supplier offer? What functionality, availability and support service levels does the supplier offer ? Is the supplier regularly subjected to external security audit or certification processes ? If so, provide the latest report / certificate
Software | Organisational | Do the procured deliverables relate to the customisation of software, which increases the risk to the timely and successful provision of the deliverables?

## Telco
Category | Risk Type | Considerations
Telco | Service Level Agreement | If the supplier is a Carrier Service Provider the Agency/customer needs to ensure that the supplier has a back to back arrangement between the Carrier and supplier. For example: Suppliers delivering NBN as a service and NBN is capable of delivering what is being offered. Interdependancy between NBN and Service providers. The more suppliers in the chain, the higher the risk
Telco | Data Sovereignty | Subject to the laws of Australia. Agencies best interest to ensure that the data that might be part of a project, is subject to the laws of Australia and not to another country. For example - backing up data in another country could lead to potential issues if there is a system failure.
Telco | Data Security | Data privacy and control. Sometimes data is stored offshote. If data is stored or accessed from offshore. If it is offshore, what kind of security restrictions are in place. What are the laws. If the data is accessed from abroad - agency needs to understand what the data is being used for and if it can be stored locally for that part of the process. Ensure data privacy is controlled i.e. to ensure that people within the suppliers company can't access the data and use it for an inappropriate purpose.
Telco | Financial | Financial stability of the suppliers being contracted. Not a high risk with larger organisations, more of a risk with small organisations. Product liabilty and professional indemnity needs to be ensured. Address those risks ongoing, a supplier on the scheme (or buy.nsw) is only checked at the time of registration. If a supplier goes into administation (or close to it) this is a risk.
Telco | Location | Customer Contract for a site to be connected. The specific site of the location can have an impact on the cost of the installation, particularly unforseen or additional future costs. Often once installation is completed there are additonal costs on top of the original calculations. If these costs come at a later point there is a potential that the tender assessment originally completed can become invalid.
Telco | Termination costs | When a site gets closed down there is a termination cost related to the site. This depends on the remaining length of contract and what is remaining to be paid. Examples of when this occurs: - An agencies business requirements change and they shut it down - The service provider did not meet the service level agreement - Machinary of government changes. Due to these activities there is a charge payable, this needs to be addressed in the contracting stage. The potential of this risk occuring is high and impact is relatively low
Telco | Step Down pricing clauses | Costs between contracts can occur if provisions are not built into the contract. For example:if a contract is for two years and the agency chooses not to renew after that period, but waits six months to transfer to a new supplier there is potential risk of increased costs. During this six months Agencies may be paying a higher cost to the incumbent supplier. In this scenario customers should consider step down pricing and consider the implictions of not paying or renewing on time and how this will impact the business.
Telco | Transition Out (Exit Strategy) | A transition out or exit strategy will reduce unexpected costs between contracts. Generally when a contract is executed this is not thought about. Incur addition expense. Certain connection equipment at an agencies site that was paid for monthly, mayt have to be paid again in the future from another supplier. Fixed data, fixed voice - need to add specific components into the contract.
Telco | Reputational Risk | If there are issues with suppliers products or with SLA's this can have a negative impact on an agencies reputation. For example, if a supplier does not follow its contract implementation schedule then the agency may face negative reprocautions from its customers (eg NSW citizens). It is recommended to include clauses on late/no delivery of service implications.
Telco | Efficiency & Reliability of Services | What are the supplier’s technical offerings? How is the supplier’s infrastructure maintained ? What physical and technological protections does the supplier have in place to reduce the risk of service disruptions and downtime ? What mechanisms does the supplier have in place in relation to disaster recovery to ensure services are quickly restored if there are availability and reliability issues ? What type of business continuity arrangements does the supplier have to ensure services continue to operate ? What support services (e.g. helpdesk) does the supplier offer? What functionality, availability and support service levels does the supplier offer ? Is the supplier regularly subjected to external security audit or certification processes ? If so, provide the latest report / certificate

## Hardware
Category | Risk Type | Considerations
Hardware | Organisational/ Technical | Has the procurement need been properly identified? Sometimes there might be an urgency to buy hardware and as a result, an agency maybuy too many laptops or workstations then later the agency might realise they need software licenses to run these hardware i.e. buying too many hardware systems will drive organisation costs up and lead to the waste of funds (procuring too little to too much results in a falsely-forecast figure) - it could end up with an inaccurate cost-estimate at procurement resulting reapproval / allocation of additional budget/ funding etc.
Hardware | Organisational/ Technical | Are there tight timelines? Is there a high probability that the business unit expect the supplier to deliver the hardware and install it for them in a very short period of time? i.e. tight timelines in procurement process push many potential vendors away from tender bid and it reduces the agency's ability to select the right vendor. It may expose the agency to risk of implementation if the winning supplier is unable to deliver on those tight deadlines. The supplier’s failure to deliver the procure Hardware on time will lead to delays and set programs back.
Hardware | Scope of Work | Are there specific/technical purposes for the procurement of this hardware? Is this bespoke hardware? The possible risk is that the hardware/replacement parts are not fit for purpose or the technical specifications have not been appropriately communicated to the supplier. One of the biggest challenge is to define scope of work and the deliverables . Leaving a number of key matters, such as deliverables, milestone dates and associated pricing, to subsequent agreement creates significant operational risks. While it may seem innocuous to agree to agree in good faith, such understandings do not create enforceable obligations and are only acceptable where the contract includes a right to terminate the contract early (without penalty) if those matters cannot be agreed. These termination provisions are rarely acceptable to suppliers as they create a high level of commercial uncertainty. It is recommended to undertake an implementation planning study prior to procurement activities.
Hardware | Organisational/ Technical | What are the specific technical procurement requirements? The possible risk is that the hardware/replacement parts do not comply with the technical requirements
Hardware | Organisational/ Technical | Does the hardware require specific installation? Does the engagement involve a service provider on site? (and what is the frequency?) The possible risk is that there could be physical damage to other devices or cabling if the service provider will access or alter exisiting structures, infrastructure or plant services
Hardware | Privacy | Does the engagement or contract require collecting or storing of Personally Identifiable Information data? This is is any data that could potentially identify a specific individual. Any information that can be used to distinguish one person from another and can be used for de-anonymizing anonymous data can be considered PII. Privacy and security clauses in an agreement/contract can be used to mitiate this risk. Agencies might need to ensure this data has been correctly classified and ensure Privacy legislation is complied with

## Cloud
Category | Risk | Considerations
Cloud | Legal /organisational | Cloud solutions often appear to have lower initial cost but solutions migh include hidden costs. Some considerations will include how to address risks with considering diﬀerent deployment models as well as migration types? The starting point might favour the vendor, resulting in a potential misalignment with agency's requirements.
Cloud | Technical/ organisational | Other challenging aspects for cloud is the Service Level Agreement i.e. to achieve specific uptime and/or performance-service-level guarantees - these might only be provided through a website and it is often a changeable URL link. Agencies should be aware of the performance service levels required and ensure that they are documented contractually
Cloud | Financial/ legal / organisational | Business Continuity / disaster recovery - Cloud ( IaaS, PaaS & SaaS) might not contain any provisions about disaster recovery or provide financially backed recovery time objectives i.e. some infrastructure-as-a-service (IaaS) providers might not back up customer data. Confirmation is needed that provider has a suitable API or other mechanism to accommodate the agency's needs in terms of disaster recovery.

## ICT Consultancy
Category | Risk | Considerations
ICT Consultancy | Financial | The total contract value can incrementally increase over time and there is a possibility that it may exceed the engagement cost before renewal
ICT Consultancy | Financial | Limitation of Liability caps for multiple fees paid on multiple agreements
ICT Consultancy | Financial | Rate creep and competition
ICT Consultancy | Delivery | Scope of work- For example, receiving a good report depends in part upon a clear specification of needs to the consultant , inability to define the the nature of the problem involve significant investments of time, money and personnel without any guarantee of a successful out- come. One of the biggest challenge consultant often give blanket solutions to the problems without customising them to the organisational needs.
ICT Consultancy | Delivery | Does the consultant have the necessary back-up facilities / plan? any conflict of interest or perceived conflict of interest? a clear indication of what is required by way of the end product (plan, contract, drawings, report, etc.? a time scale for the work with a target starting date and a programme for any intermediate stages, if required? a list of the parameters - financial limitations, previous commitments, influence, established plans and policies? an indication of the budget available for the said project?